Chrystalls Stopbank Upgrade

Summary of Estimated Costs

DESIGN AND CONSTRUCT

| ##### 1998/99 | ###### Budget | ###### Actual | ###### Difference |
| --- | --- | --- | --- |
| Land access negotiations, legal and survey fees etc. | 13,050 | 7,445 | 5,605 |
| Design and Consents | 52,450 | 57,794 | (5,344) |
| ##### Subtotal | $65,500 | ###### $65,239 | $239 |
| ##### 1999/2000 |  | ###### Estimated |  |
| Engineering Consultants | 0 | 42,000 | (42,000) |
| WRC Staff input | 15,404 | 8,000 | 7,404 |
| Contingency | 0 | 10,000 | (10,000) |
| Construction (incl. 10% contingency) | $466,496 | $415,690 | 50,806 |
| ### Subtotal | $481,900 | $475,690 | $6,210 |
| # Design and Construct Subtotal | $547,400 | $540,929 | $6,471 |

LAND PURCHASE

| #### 1998/99 | #### STAGE 1 LAND |  | ###### Budget | ###### Actual | ###### Difference |
| --- | --- | --- | --- | --- | --- |
|  | Land Purchase |  | 18,000 | 0 | 18,000 |
| 1999/2000 | STAGE 1 LAND |  |  | ###### Estimated |  |
|  | Land access negotiations, legal and survey fees etc. |  | 0 | 17,000 | (17,000) |
|  | Land Purchase |  | 0 | 35,000 | (35,000) |
|  | # Stage 1 Land Subtotal |  | $18,000 | $52,000 | ($34,000) |
|  | ## OR |  |  |  |  |
|  | STAGES 1 & 2 LAND |  |  | ###### Estimated |  |
|  | Land access negotiations, legal and survey fees etc. |  | 0 | 24,000 | (24,000) |
|  | Land Purchase |  | 0 | 128,000 | (128,000) |
|  |  | ### Stages 1 & 2 Land Subtotal | $18,000 | $152,000 | ($134,000) |

TOTAL

|  | ###### Budget | ###### Estimated | ###### Difference |
| --- | --- | --- | --- |
| ## STAGE 1 | $565,400 | $592,929 | ($27,529) |
| INCLUDING STAGE 2 LAND | $565,400 | $692,929 | ($127,529) |

## Budget Summary

1998/99 Design and Consents	$  65,500

1998/99 Asset Purchase	$  18,000

1999/2000 Construction	$481,900